## Summary
HAZOP preparation — System 20 (functional loops)
Node | Members | Rows | Rows w/ safeguard | proposed | reviewed | rejected
loop 20-2000 | 20-FIC2000, 20-FT2000, 20-FV2000, 20-FY2000 | 4 | 0 | 4 | 0 | 0
loop 20-2016 | 20-PI2016, 20-PT2016 | 2 | 0 | 2 | 0 | 0
loop 20-2060 | 20-TAHH2060, 20-TI2060, 20-TT2060 | 2 | 0 | 2 | 0 | 0
loop 20-2200 | 20-LIC2200, 20-LIC2200A, 20-LIC2200B, 20-LV2200A, 20-LV2200B, 20-LY2200A, 20-LY2200B | 2 | 0 | 2 | 0 | 0
loop 20-2202 | 20-HS2202, 20-HS2202A, 20-HS2202B, 20-XV2202A, 20-XV2202B, 20-XY2202A, 20-XY2202B, 20-ZL2202A, 20-ZL2202B, 20-ZS2202A, 20-ZS2202B | 4 | 4 | 4 | 0 | 0
AI-prepared draft from extracted P&ID/SCD data — for HAZOP team review, not a completed study.

## loop 20-2000
Node: loop 20-2000
Members: 20-FIC2000, 20-FT2000, 20-FV2000, 20-FY2000
Deviation | Causes | Consequences | Safeguards | S | L | Risk | Recommendation | Action party | Status
No flow | 20-FIC2000: wrong output; 20-FIC2000: tuning drift; 20-FV2000: sticks; 20-FV2000: wrong position; blocked line / closed valve (generic); pump/compressor stop (generic) | loss of process function (generic); functions affected: 20-FIC2000, 20-FV2000, 20-FY2000 | (none found in extraction — verify) | [5 empty] | proposed
Low flow | 20-FIC2000: wrong output; 20-FIC2000: tuning drift; 20-FV2000: sticks; 20-FV2000: wrong position; partial blockage / fouling (generic) | reduced capacity (generic); functions affected: 20-FIC2000, 20-FV2000, 20-FY2000 | (none found in extraction — verify) | [5 empty] | proposed
High flow | 20-FIC2000: wrong output; 20-FIC2000: tuning drift; 20-FV2000: sticks; 20-FV2000: wrong position; control valve fully open (generic) | possible downstream overload (generic); functions affected: 20-FIC2000, 20-FV2000, 20-FY2000 | (none found in extraction — verify) | [5 empty] | proposed
Reverse flow | 20-FIC2000: wrong output; 20-FIC2000: tuning drift; 20-FV2000: sticks; 20-FV2000: wrong position; check-valve failure / pressure reversal (generic) | possible contamination / backflow to upstream (generic); functions affected: 20-FIC2000, 20-FV2000, 20-FY2000 | (none found in extraction — verify) | [5 empty] | proposed

## loop 20-2016
Node: loop 20-2016
Members: 20-PI2016, 20-PT2016
Deviation | Causes | Consequences | Safeguards | S | L | Risk | Recommendation | Action party | Status
High pressure | blocked outlet (generic); upstream pressure source (generic) | possible overpressure of section (generic) | (none found in extraction — verify) | [5 empty] | proposed
Low pressure | upstream supply loss (generic); leak / rupture (generic) | loss of process function / possible gas breakthrough (generic) | (none found in extraction — verify) | [5 empty] | proposed

## loop 20-2060
Node: loop 20-2060
Members: 20-TAHH2060, 20-TI2060, 20-TT2060
Deviation | Causes | Consequences | Safeguards | S | L | Risk | Recommendation | Action party | Status
High temperature | loss of cooling (generic) | possible material/design-limit exceedance (generic) | (none found in extraction — verify) | [5 empty] | proposed
Low temperature | JT-cooling on depressurisation (generic); loss of heating (generic) | possible hydrate formation / brittle fracture risk (generic) | (none found in extraction — verify) | [5 empty] | proposed

## loop 20-2200
Node: loop 20-2200
Members: 20-LIC2200, 20-LIC2200A, 20-LIC2200B, 20-LV2200A, 20-LV2200B, 20-LY2200A, 20-LY2200B
Deviation | Causes | Consequences | Safeguards | S | L | Risk | Recommendation | Action party | Status
High level | 20-LIC2200: wrong output; 20-LIC2200: tuning drift; 20-LIC2200A: wrong output; 20-LIC2200A: tuning drift; 20-LIC2200B: wrong output; 20-LIC2200B: tuning drift; outlet restriction (generic); inflow exceeds outflow (generic) | possible carry-over / overfill (generic); functions affected: 20-LIC2200, 20-LIC2200A, 20-LIC2200B, 20-LV2200A, 20-LV2200B, 20-LY2200A, 20-LY2200B | (none found in extraction — verify) | [5 empty] | proposed
Low level | 20-LIC2200: wrong output; 20-LIC2200: tuning drift; 20-LIC2200A: wrong output; 20-LIC2200A: tuning drift; 20-LIC2200B: wrong output; 20-LIC2200B: tuning drift; loss of feed (generic); excess drainage (generic) | possible gas blow-by to downstream (generic); functions affected: 20-LIC2200, 20-LIC2200A, 20-LIC2200B, 20-LV2200A, 20-LV2200B, 20-LY2200A, 20-LY2200B | (none found in extraction — verify) | [5 empty] | proposed

## loop 20-2202
Node: loop 20-2202
Members: 20-HS2202, 20-HS2202A, 20-HS2202B, 20-XV2202A, 20-XV2202B, 20-XY2202A, 20-XY2202B, 20-ZL2202A, 20-ZL2202B, 20-ZS2202A, 20-ZS2202B
Deviation | Causes | Consequences | Safeguards | S | L | Risk | Recommendation | Action party | Status
No flow | blocked line / closed valve (generic); pump/compressor stop (generic) | loss of process function (generic); functions affected: 20-HS2202, 20-HS2202A, 20-HS2202B, 20-XV2202A, 20-XV2202B, 20-XY2202A, 20-XY2202B; safety functions in node: 20-HS2202, 20-HS2202A, 20-HS2202B, 20-XV2202A, 20-XV2202B, 20-ZL2202A, 20-ZL2202B, 20-ZS2202A, 20-ZS2202B | 20-XV2202A (⚠ same loop — verify independence), 20-XV2202B (⚠ same loop — verify independence) | [5 empty] | proposed
Low flow | partial blockage / fouling (generic) | reduced capacity (generic); functions affected: 20-HS2202, 20-HS2202A, 20-HS2202B, 20-XV2202A, 20-XV2202B, 20-XY2202A, 20-XY2202B; safety functions in node: 20-HS2202, 20-HS2202A, 20-HS2202B, 20-XV2202A, 20-XV2202B, 20-ZL2202A, 20-ZL2202B, 20-ZS2202A, 20-ZS2202B | 20-XV2202A (⚠ same loop — verify independence), 20-XV2202B (⚠ same loop — verify independence) | [5 empty] | proposed
High flow | control valve fully open (generic) | possible downstream overload (generic); functions affected: 20-HS2202, 20-HS2202A, 20-HS2202B, 20-XV2202A, 20-XV2202B, 20-XY2202A, 20-XY2202B; safety functions in node: 20-HS2202, 20-HS2202A, 20-HS2202B, 20-XV2202A, 20-XV2202B, 20-ZL2202A, 20-ZL2202B, 20-ZS2202A, 20-ZS2202B | 20-XV2202A (⚠ same loop — verify independence), 20-XV2202B (⚠ same loop — verify independence) | [5 empty] | proposed
Reverse flow | check-valve failure / pressure reversal (generic) | possible contamination / backflow to upstream (generic); functions affected: 20-HS2202, 20-HS2202A, 20-HS2202B, 20-XV2202A, 20-XV2202B, 20-XY2202A, 20-XY2202B; safety functions in node: 20-HS2202, 20-HS2202A, 20-HS2202B, 20-XV2202A, 20-XV2202B, 20-ZL2202A, 20-ZL2202B, 20-ZS2202A, 20-ZS2202B | 20-XV2202A (⚠ same loop — verify independence), 20-XV2202B (⚠ same loop — verify independence) | [5 empty] | proposed